## Custom Snapshot
Check List For Custom Snapshot
Project Name: | Urban SDK |  |  |  |  | No. of testcase: | 11
Module Name: | Custom Snapshot |  |  |  |  | No. of Passed test: | 0
Reference Document / Link: | [5 empty] | No. of Failed test: | 1
Created By: | Benjamin Bentil |  |  |  |  | Last Updated: | 22-Jul-26
Date of Creation: | 22-Jul-26
Requirement ID | Requirement Description | Test Case ID | Steps | Module Impacts | Applicable Roles | Verified | Expected Results | Status | Bug Title
Custom Snapshot modal opens from Time filter | The system shall open the Custom Snapshot modal when the user taps Custom Range from the Time filter. | CS_001 | 1. Navigate to Insights. 2. Tap 'Time' filter. 3. Tap 'Custom Range'. | Insights | Owner, Admin, Analyst | Not Verified | Custom Snapshot modal opens showing Step 1 (Location scope), Step 2 (Filters), Step 3 (Dates). | Not Started
Location scope reflects active project area | The system shall display the currently active location scope (e.g. Jax Beach) in Step 1 of the Custom Snapshot modal. | CS_002 | 1. Open Custom Snapshot modal. 2. Review 'Location scope' card (Step 1). 3. Tap 'Edit location'. | Insights | Owner, Admin | Not Verified | Current location (e.g. Jax Beach) displays correctly; user can edit/change the location scope. | Not Started
Filters scope reflects active filters | The system shall display currently applied filters (e.g. Road Safety, Countermeasure) in Step 2 of the modal. | CS_003 | 1. Open Custom Snapshot modal. 2. Review 'Filters' card (Step 2). 3. Tap 'Edit filters'. | Insights | Owner, Admin, Analyst | Not Verified | Filters step shows current applied filters (or 'No filters applied'); user can edit filters from here. | Not Started
Specific Dates selection works | The system shall allow the user to select one or more specific dates in Step 3 of the Custom Snapshot modal. | CS_004 | 1. Open Custom Snapshot modal. 2. Under Step 3, select 'Specific Dates'. 3. Pick one or more dates from calendar. | Insights | Owner, Admin, Analyst | Not Verified | Selected date(s) highlight on calendar; selected date count updates (e.g. '1 selected date'). | Not Started
Custom Range date selection works | The system shall allow the user to select a start and end date under Custom Range in Step 3. | CS_005 | 1. Open Custom Snapshot modal. 2. Under Step 3, select 'Custom Range'. 3. Tap 'Select date' (start). 4. Tap 'Select date' (end). | Insights | Owner, Admin, Analyst | Not Verified | Start and end date pickers open correctly; selected range displays in both fields. | Not Started
Snapshot request submits successfully | The system shall queue a snapshot request once Location, Filters, and Dates are configured and submitted. | CS_006 | 1. Complete Steps 1-3. 2. Tap the submit/confirm action to request the snapshot. | Insights | Owner, Admin | Not Verified | Confirmation message appears (e.g. 'Custom Snapshots will take 5 min to process...'); request is queued. | Not Started
Snapshot processing notification is received | The system shall notify the user via email and/or in-app once a submitted snapshot has finished processing. | CS_007 | 1. Submit a snapshot request. 2. Wait ~5 minutes. 3. Check email and in-app notifications. | Insights | Owner, Admin | Not Verified | User receives a notification (email and/or in-app) once the snapshot is ready. | Not Started
Completed snapshot displays accurate data | The system shall display data in the completed snapshot matching the selected location, filters, and date range. | CS_008 | 1. Open notification or navigate to Snapshots. 2. Locate the completed custom snapshot. 3. Open it. | Insights | Owner, Admin, Analyst | Not Verified | Snapshot opens and displays data matching the selected location, filters, and date range. | Not Started
Closing modal does not reset underlying Time filter | The system shall preserve the previously active Time filter when the Custom Snapshot modal is closed via the X button. | CS_009 | 1. Open Custom Snapshot modal. 2. Complete Step 1 and 2. 3. Tap the 'X' close button. | Insights | Owner, Admin, Analyst | Verified | Modal should close without resetting the underlying Time filter or other unrelated settings. | FAIL | Custom Range X button resets entire Time filter panel
Validation blocks submission with no dates selected | The system shall prevent snapshot submission and show a validation message when no dates are selected in Step 3. | CS_010 | 1. Open Custom Snapshot modal. 2. Leave Step 3 (Dates) with 0 selected dates. 3. Attempt to submit. | Insights | Owner, Admin, Analyst | Not Verified | System should prevent submission and show a clear validation message indicating dates are required. | Not Started
Limited mode messaging is accurate | The system shall clearly explain in the modal that location and filter scope are inherited from the current page. | CS_011 | 1. Open Custom Snapshot modal. 2. Review the 'Limited mode' notice text. | Insights | Owner, Admin, Analyst | Not Verified | Message clearly explains that location and filter scope are taken from the current page, and only the date selector is editable here. | Not Started

## Tasks
Check List For Tasks
Project Name: | Urban SDK |  |  |  |  | No. of testcase: | 15
Module Name: | Tasks |  |  |  |  | No. of Passed test: | 0
Reference Document / Link: | [5 empty] | No. of Failed test: | 3
Created By: | Benjamin Bentil |  |  |  |  | Last Updated: | 22-Jul-26
Date of Creation: | 22-Jul-26
Requirement ID | Requirement Description | Test Case ID | Steps | Module Impacts | Applicable Roles | Verified | Expected Results | Status | Bug Title
Task creation succeeds with correct stage placement | The system shall allow a new task to be created and placed correctly under the selected stage. | TSK_001 | 1. Navigate to Tasks tab. 2. Tap '+ New Task'. 3. Title it 'Public Outreach: [Street Name] Complaint Issue'. 4. Set Stage to 'Review', Priority to 'Medium'. 5. Save. | Tasks | Owner, Admin, Analyst | Not Verified | Task is created successfully, titled correctly, and appears under the 'Review' stage column/list with no errors. | Not Started
Task opens and displays full detail | The system shall open a task and display all associated fields without error. | TSK_002 | 1. Navigate to Tasks tab. 2. Tap on a task title/row to open it. 3. Confirm task details load correctly. | Tasks | Owner, Admin, Analyst | Not Verified | Task detail view opens showing all fields (Title, Stage, Priority, Assignee, Due Date, etc.) without errors. | Not Started
Task edits save and reflect across views | The system shall save edits made to an existing task and reflect them in both List and Board views. | TSK_003 | 1. Open an existing 'Escalate: Ad Hoc' task. 2. Edit fields (e.g. Priority to 'High', Due Date). 3. Save changes. | Tasks | Owner, Admin | Not Verified | Changes save successfully and are reflected immediately in both List and Board views. | Not Started
Task deletion requires confirmation | The system shall prompt for confirmation before permanently deleting a task. | TSK_004 | 1. Open the task action menu (⋮). 2. Tap 'Delete'. 3. Confirm deletion if prompted. | Tasks | Owner, Admin | Not Verified | Task is removed from the list/board after confirmation; confirmation dialog should appear before deletion. | Not Started
Task stage updates correctly - List view | The system shall update a task's stage when changed via the Stage dropdown in List view. | TSK_005 | 1. Navigate to Tasks List view. 2. Use the Stage dropdown on a Countermeasure-related task row. 3. Change stage from 'Review' to 'Monitor'. | Tasks | Owner, Admin, Analyst | Not Verified | Task stage updates correctly to 'Monitor' and task appears under the Monitor stage grouping. | Not Started
Task moves through full lifecycle - Board view | The system shall allow a task to be dragged through all stages (Review to Monitor to Action to Complete) on the Board view. | TSK_006 | 1. Navigate to Tasks Board view. 2. Drag task card from Review to Monitor. 3. Drag from Monitor to Action. 4. Drag from Action to Complete. | Tasks | Owner, Admin, Analyst | Not Verified | Task moves through each column correctly; column counts update at every stage; final state shows task under 'Complete'. | Not Started
Task assignment updates correctly | The system shall allow a task to be assigned to a user and reflect the assignment across views. | TSK_007 | 1. Open a 'Public Outreach: [Street] Complaint Issue' task. 2. Tap the Assignee field. 3. Select a reviewer (e.g. Gayathri GSG). 4. Save. | Tasks | Owner, Admin | Not Verified | Task is assigned to the selected reviewer; Assignee column/avatar updates correctly across List and Board views. | Not Started
Task unassignment works correctly | The system shall allow a task to be returned to an 'Unassigned' state. | TSK_008 | 1. Open an assigned task. 2. Change Assignee to 'Unassigned' or clear the field. 3. Save. | Tasks | Owner, Admin | Not Verified | Task returns to 'Unassigned' state correctly. | Not Started
Filter by Priority narrows List view correctly | The system shall allow filtering the task list by Priority. | TSK_009 | 1. Navigate to Tasks List view. 2. Use the Priority filter icon. 3. Filter to 'High' priority items only. | Tasks | Owner, Admin, Analyst | Not Verified | List narrows to show only High priority tasks; count updates accordingly. | Not Started
Filter by Stage available in List view | The system shall provide a filter option on the Stage column consistent with other columns. | TSK_010 | 1. Navigate to Tasks List view. 2. Check column headers: Stage, Title, Priority, Due Date, Assignee. | Tasks | Owner, Admin, Analyst | Verified | Stage column should have a filter icon, consistent with Priority, Due Date, and Assignee columns. | FAIL | Missing filter icon on Stage column (Tasks list view)
Filter options available in Board view | The system shall provide filter controls in Board view consistent with List view. | TSK_011 | 1. Navigate to Tasks Board view. 2. Look for filter controls tied to Stage/columns. | Tasks | Owner, Admin, Analyst | Verified | Filter controls should be available in Board view, consistent with List view. | FAIL | Missing filter options in Board view (Tasks)
Export PDF completes without freezing | The system shall generate and download a PDF report from Tasks Overview without freezing the page. | TSK_012 | 1. Navigate to Tasks tab. 2. Tap Overview. 3. Tap Quick Actions. 4. Tap 'Export PDF'. 5. Wait for download. | Tasks | Owner, Admin | Verified | PDF downloads successfully without freezing the page; report renders map, summary, and chart data correctly. | FAIL | Export PDF causes page to freeze during download (Tasks Overview)
Task Summary panel reflects accurate counts | The system shall display accurate Low/Medium/High/Critical task counts in the Task Summary panel. | TSK_013 | 1. Navigate to Tasks Overview. 2. Review Task Summary panel (Low/Medium/High/Critical counts). | Tasks | Owner, Admin, Analyst | Not Verified | Counts accurately reflect current task data. | Not Started
Task Status chart reflects volume by month correctly | The system shall render the Task Status chart correctly and update it when the time interval is toggled. | TSK_014 | 1. Navigate to Tasks Overview. 2. Review 'Task Status' chart. 3. Toggle Day/Week/Month intervals. | Tasks | Owner, Admin, Analyst | Not Verified | Chart renders correctly and updates when toggling time interval. | Not Started
Refresh reloads task data cleanly | The system shall reload task data with a single clean loading and success state when Refresh is tapped once. | TSK_015 | 1. Tap the Refresh icon once. 2. Observe result. | Tasks | Owner, Admin, Analyst | Not Verified | Tasks reload cleanly with a single loading indicator and success confirmation. | Not Started